## Slide 1
CONSTRUCTEDGE CONSTRUCTION & INFRASTRUCTURE
2025 Procurement Performance
Where portfolio savings hide concentrated project, supplier, and delivery risk
Validated analysis release · 23 July 2026
Prepared by Neil Gasson

## Slide 2
PROBLEM
The portfolio average is healthy—but it masks three decision-critical pockets
Validated 2025 procurement dataset
2
Portfolio result
−$13.41M
Net under budget across 400 validated transactions. The result is real—but it is not evenly distributed.
Where leaders should look next
01 Three projects are net over budget 02 Three suppliers repeatedly price above budget 03 Delivery reliability falls to 64.29% in Finishing

## Slide 3
DATA & TOOL
The evidence passed every acceptance test before analysis began
Validated 2025 procurement dataset
3
The official dataset contains 400 distinct transactions. Instructor-approved corrections are logged at cell level; financial identities, dates, counts, totals, and Q1–Q4 were independently verified.
400
validated transactions
31 / 31
acceptance tests passed
83 / 83
independent Q1–Q4 matches

## Slide 4
Q1 · COST OVERRUNS
Only three projects are net over budget; all categories remain net under
Validated 2025 procurement dataset
4
Ranked by summed Cost Variance (CAD). Red = over budget; teal = under budget. Bar length shows absolute size.
$279.7K
Quarry Park ranks first
Calgary SE Ring Road: +$134.6K Deerfoot Trail North: +$29.1K Finishing is the closest category to zero at −$60.0K.
Chart: 
| University District | Bow River | Foothills | Stampede Park | Rocky View | Saddledome | Springbank | Deerfoot Trail North | Calgary SE Ring Road | Quarry Park
Net variance | 3.5307 | 3.4944 | 2.3253 | 1.7623 | 1.7266 | 0.52568 | 0.49258 | 0.029147 | 0.13459 | 0.27967

## Slide 5
Q2 · SUPPLIER CONSISTENCY
Three suppliers show repeatable above-budget pricing
Validated 2025 procurement dataset
5
Consistently = more than 50% of orders over budget and positive total supplier variance.
$2.02M
combined net positive variance
Houle: 63.64% above budget PCL Mechanical: 53.33% Levitt-Safety: 61.54%
Chart: 
| Houle Electric | PCL Mechanical | Levitt-Safety Calgary
Average variance | 74.5833 | 73.8991 | 7.2272

## Slide 6
Q3 · PROCUREMENT METHOD
Procurement method explains virtually none of the variance
Validated 2025 procurement dataset
6
All five observed methods are under budget on average. Their distributions overlap heavily.
p = 0.894
ANOVA on row Variance_%
η² = 0.0028
≈0.28% of differences explained
Chart: 
| 3-Quote | Direct Award | Emergency | Open Tender | Standing Offer
Average row variance | -2.3525 | -2.5218 | -2.0921 | -3.4355 | -3.4062

## Slide 7
Q4 · DELIVERED ORDERS ONLY
Delivery reliability lags in Finishing and selected suppliers
Validated 2025 procurement dataset
7
151 of 204 Delivered orders arrived on time. Pending, Cancelled, and Partially Delivered orders are excluded.
74.02%
portfolio on-time rate
Best category: Safety & Temp Works, 82.86% Worst category: Finishing, 64.29% Worst supplier: Tremco, 42.86%
Chart: 
| Safety & Temp | Civil Works | MEP Electrical | MEP Mechanical | Concrete & Struct. | Finishing
On-time rate | 82.8571 | 80 | 75.7576 | 75 | 67.7419 | 64.2857

## Slide 8
TOP 3 RECOMMENDATIONS
Focus action where the same risk repeats
Validated 2025 procurement dataset
8
01
Launch targeted commercial reviews with the suppliers that meet the consistently-above-budget rule.
3 suppliers qualify: Houle Electric, PCL Mechanical, Levitt-Safety Calgary. Their combined net positive variance is $2,022,856.51.
$1.01M scenario
02
Add pre-award variance thresholds and monthly exception reviews for the three projects with positive net cost variance.
3 projects are net over budget: Quarry Park Mixed-Use Development, Calgary SE Ring Road Extension, Deerfoot Trail Widening - North. Combined net overrun is $443,408.60.
$221.7K scenario
03
Create supplier delivery scorecards and corrective-action plans for material categories and suppliers below the Delivered-only portfolio benchmark.
The Delivered-only on-time rate is 74.02%. 2 material categories are below that benchmark.
≈7 more on-time deliveries

## Slide 9
LIMITATIONS & IMPLEMENTATION
Use the findings decisively—with four guardrails
Validated 2025 procurement dataset
9
What the data does not prove
• The analysis covers 2025 only • Method comparisons are observational, not causal • Imputed lead times affect two Civil Works records • Recommendation impacts are directional, overlapping scenarios
What to do in the next 90 days
0–30 days Launch supplier reviews and assign project thresholds 31–60 days Publish delivery scorecards by supplier and category 61–90 days Review exceptions, measure movement, and reset targets

## Slide 10
DECISION
Act where risk repeats—not where the portfolio average looks comfortable.
Target three suppliers · Protect three projects · Raise delivery reliability
Validated release · 31/31 acceptance tests passed